## Remaining Tasks
Mandatory Tasks
Number | Task | Worker | Status | Note
1 | Product Genres | Both | Finished | Movies/TV Series have genres.
2 | View Product | Not Assigned | Not Started | Front-End Part
3 | Buying Items From Cart | Svetoslav | Finished | Users can buy items from cart.
4 | Adding Products | Not Assigned | Not Started | Administrator method
5 | Editing Product Info | Not Assigned | Not Started | Administrator method
6 | Putting Products On Promotion | Not Assigned | Not Started | Administrator method
7 | Add Administrators To project | Svetoslav | Not Started | Pojo / Dao / Manager
8 | Searching for products by name | Not Assigned | Not Started
9 | Filtering products | Not Assigned | Not Started | Filter products by: year, price, genre, rating etc. (we have an example SQL built for this type of filtering)
10 | Product Ordering | Not Assigned | Not Started | Complementary task to Task # 9. Both tasks should probably use 1 method
11 | Notifications for products which are about to expire | Not Assigned | Not Started | Sending emails to users that have 1 day left until some of their products expire. Group all expiring products in 1 email. (Can build a Map<userId, List<productId>> and create email message from there).
12 | Notifications for products that have expired??? | Not Assigned | Not Started | Same as 11 for expired products.
13 | Edit User's information | Not Assigned | Not Started | Editting user's personal info (without the password??)
14 | Resetting user's password | Not Assigned | Not Started | Send users an email with a reset password link??
15 | Handle all exceptions in servlets and methods | Not Assigned | Not Started
16 | Rename all servlet mappings | Not Assigned | Not Started
BONUS TASKS
Number | Task | Worker | Status | Note
1
2